## 01_Overview
RMMS 2026 — Phase 1 Plan
Document v1.0 ¦ Plan generated 2026-05-22
PROJECT CONTEXT
Project name | RMMS 2026 (rewrite) — Retail Merchandiser Management System
Business model | Internal product — 1 customer (own company)
Users | PG, Leader, Admin, BUH
Phase 1 strategy | Split into Phase 1A + Phase 1B for internal staged release; single acceptance gate at end of 1B
TEAM SETUP
Team size | 2 Senior Developers (generalist)
PM role | 1 dev kiêm PM/PO (-20% dev capacity)
Design | Dev tự design UI (UI đơn giản)
QA | Dev tự test (built into sprint capacity)
DevOps | Dev tự setup (Sprint 0)
TECH STACK
Backend | .NET 8 + EF Core + PostgreSQL 16 + Redis 7 + Hangfire + SignalR
Web Admin/BUH | Next.js 14 + TypeScript + Ant Design Pro + TanStack Query + Zustand
Mobile | Flutter 3.x + Riverpod + Dio + Hive (offline draft)
Infrastructure | Ubuntu 22.04 + Docker Compose + Caddy + Vultr Singapore VPS
Face Recognition | FPT.AI Face (VN, ~500đ/verify) — TBD in Sprint 0
Push notification | Firebase Cloud Messaging (free tier)
Email | SendGrid or AWS SES — TBD
File storage | AWS S3 or MinIO self-hosted
KEY DATES & DURATION
Sprint length | 2 weeks
Sprint 0 (setup) | 2 weeks
Phase 1A duration | 10 sprints (~5 months) — Internal release
Phase 1B duration | 8 sprints (~4 months) — Final UAT & acceptance
Total duration | ~10 months from kickoff
SCOPE SUMMARY
Total modules | 16
Phase 1A modules | 11 (Identity, Device, Org, Attendance, Face, Schedule, Leave/OT, Approval, Team Monitoring, Audit, Notification-basic)
Phase 1B modules | 6 (Product, Form Engine, Visit Plan, Document, Notification-full, Dashboard-full)
Acceptance criteria | 35 criteria (full list in 02_Modules)
ACCEPTANCE STRATEGY
Phase 1A end | Internal UAT — feedback collected, NO formal acceptance
Phase 1B end | Formal acceptance gate — full 35 criteria must pass
UAT period | Last 2 sprints reserved for UAT + bug fix only (no new features)
OUT OF SCOPE PHASE 1
Excluded items | Salary calc, Beacon, Target, KPI, Gifts, Promotions, Invoice, Old sale reports, Migration, Full offline app, Offline check-in, Excel import

## 02_Modules
MODULE BREAKDOWN — Phase 1A + 1B
No. | Module | Scope summary | Priority | Complexity | Est. dev-days | Phase | Dependencies | Acceptance criteria refs
1 | Identity & Access | Email registration (PG), assigned accounts (Leader/Admin/BUH), login/logout, role-based permissions, password reset, login history | P0 | Medium | 18 | 1A | — | AC-1, AC-2
2 | Device Management | Single-device login enforcement for PG, device change request flow, Leader/Admin approval, device history log | P0 | Medium | 14 | 1A | M1 | AC-3
3 | Organization & Assignment | Manage PG/Leader/BUH, Store (with GPS coords), Area, Category. Assign PG↔Leader, PG↔Store, PG↔Category | P0 | Medium | 20 | 1A | M1 | —
4 | Product Master | Admin CRUD Product (category, brand, SKU). Used as data source for Form Engine product selector | P1 | Low | 8 | 1B | M3 | AC-25
5 | Attendance & Anti-Fraud | Check-in/out at assigned store, GPS validation (300m threshold, fake GPS block), selfie capture, store photo with EXIF, attendance history, status tracking | P0 | High | 35 | 1A | M1, M3, M6, M16 | AC-4, AC-5, AC-6, AC-9, AC-10
6 | Face Verification | PG face enrollment, mandatory face check at check-in/out, 3rd-party Face API integration (FPT.AI), fail → Admin Review | P0 | High | 22 | 1A | M1, M5 | AC-7, AC-8, AC-11, AC-12, AC-13
7 | Work Schedule | Register schedule by day/week/month, multi-shift/day, multi-store/day, edit unconfirmed days, send for approval, version handling (old schedule active while edit pending) | P0 | High | 28 | 1A | M1, M3, M9 | AC-14, AC-15
8 | Leave & OT | Create leave/emergency leave/OT requests, reason input, link emergency leave to check-out, history view | P0 | Medium | 16 | 1A | M1, M9 | AC-16
9 | Approval Workflow | Shared workflow engine: PG→Leader, Leader→BUH. BUH email-link approval (no login required). Hybrid (inline + detail view). Mandatory reason on reject. Admin override with audit. Used by Schedule/OT/Leave/Visit Plan | P0 | High | 30 | 1A | M1 | AC-17, AC-18, AC-19
10 | Form Engine | Form Builder (12+ input types), 9 form templates, configurable rules (target users, time, store/GPS/check-in required, scoring, randomization, results visibility, edit-after-submit), assignment by role/user/store/area/category, offline draft, versioning on edit-after-publish | P0 | Very High | 55 | 1B | M1, M3, M4 | AC-20, AC-21, AC-22, AC-23, AC-24
11 | Visit Plan & Execution | Leader creates visit plan (date, stores, tasks/forms), sends to BUH approve, executes visit, submits post-visit report via Form Engine | P0 | Medium | 20 | 1B | M1, M3, M9, M10 | AC-28, AC-29, AC-30
12 | Team Monitoring / PG Online | List PG/Leader online, check-in/out status today, Leader sees own PGs, Admin/BUH see by permission, manual refresh, last-update timestamp | P0 | Medium | 14 | 1A | M3, M5 | AC-26, AC-27
13 | Document Center | Public/private folders, Admin upload, assign to user/role, support PDF/image/text, search by name, payslip as private file per user | P1 | Medium | 16 | 1B | M1, M3, M14 | AC-31, AC-32
14 | News & Notification | Admin creates news, in-app + push + email channels, classification, read/unread tracking, important news with read confirmation, badge | P0 (basic) / P1 (full) | Medium | 22 | 1A (basic), 1B (full) | M1 | AC-33, AC-34
15 | Dashboard & Reports | Phase 1 required: PG/Leader Online + check-in/out today. Reports by module: attendance, anomalies, face fail, GPS violation, fake GPS, schedule, leave/OT, pending approval, form, visit. Export per report | P0 (basic) / P1 (full) | Medium | 22 | 1A (basic), 1B (full) | M3, M5, M7, M8, M10, M11 | AC-27
16 | Admin Review & Audit Log | Admin Review cases: GPS>300m, face fail, device change, manual check-in/out. Actions: approve/reject/note/request more. Comprehensive audit log for all critical actions | P0 | High | 25 | 1A | M1, M5, M6, M2 | AC-11, AC-12, AC-13, AC-19, AC-35
| TOTAL Phase 1A dev-days |  |  |  | 240
| TOTAL Phase 1B dev-days |  |  |  | 125
| GRAND TOTAL dev-days |  |  |  | 365
LEGEND
| Priority | P0 (must) | P1 (should) | P2 (nice)
| Phase | 1A | 1B | Mixed

## 03_Sprints
SPRINT BREAKDOWN — Phase 1A (10) + Phase 1B (8) + Sprint 0 setup
Sprint | Phase | Sprint goal | Key user stories / deliverables | Tasks (BE / FE / Mobile / QA / DevOps) | Story pts | Dev-days | Modules touched
S0 | Setup | Foundation & infra ready | • Setup repo (BE/Web/Mobile mono-repo or 3 repos) • CI/CD pipeline (GitHub Actions) • VPS provisioning + Docker Compose • PostgreSQL + Redis setup • Apple Developer + Google Play accounts • Domain + SSL (Caddy auto) • Sentry monitoring • Decide: Face Recognition vendor | BE: project skeleton, EF Core, base auth scaffolding FE: Next.js init, Ant Design Pro setup, i18n config Mobile: Flutter init, dependency setup, i18n DevOps: VPS setup, Docker, Nginx/Caddy, CI/CD QA: test strategy doc | 0 | 12 | Foundation
S1 | 1A | Identity & Device foundation | • PG email registration with verification • Login/logout (all roles) • JWT + refresh token • Password reset flow • Single-device enforcement logic • Login history | BE: User entity, auth endpoints, refresh token, password reset Mobile: Login/register screens, token storage Web: Login screen for Admin/BUH QA: auth flow test cases | 21 | 18 | M1
S2 | 1A | Org structure & assignment | • PG/Leader/BUH CRUD (Admin web) • Store CRUD with GPS coords • Area & Category CRUD • Assign PG↔Leader • Assign PG↔Store (multi-store) • Device change request flow | BE: Org entities, assignment relations, device approval endpoints Web: Admin CRUD screens Mobile: device-change notification handling QA: assignment edge cases | 20 | 18 | M2, M3
S3 | 1A | Attendance core (no Face) | • Check-in screen on Mobile (PG/Leader) • Store auto-detection (assigned) • GPS validation (300m, fake GPS detect) • Selfie capture • Store photo with EXIF • Check-in/out without Face Recognition first • Attendance history view | BE: Attendance entity, GPS validation logic, fake GPS detection (mock_location flag, plugin-based) Mobile: check-in flow, camera, geolocator, exif_image Web: attendance list (read-only) QA: GPS edge cases, fake GPS | 21 | 20 | M5
S4 | 1A | Face Verification + Attendance integration | • PG face enrollment screen • FPT.AI Face API integration • Mandatory face check at check-in/out • Face fail → Admin Review queue • Tie attendance status to face result • 60-min early check-in, 5-min late marking | BE: Face API client, enrollment endpoint, verify endpoint, status state machine Mobile: face enrollment flow, face capture during check-in Web: Admin Review queue UI QA: face accuracy testing on real devices | 21 | 22 | M5, M6
S5 | 1A | Work Schedule | • Calendar view (month/week/day) Mobile • Register schedule by day/week/month • Multi-shift, multi-store per day • Send for approval • Edit unconfirmed days • Versioning (old active while edit pending) • Schedule states | BE: Schedule entity, shift entity, state machine, version logic Mobile: schedule UI, multi-select dates Web: schedule overview for Admin/Leader QA: complex date edge cases | 20 | 22 | M7
S6 | 1A | Approval Workflow Engine | • Generic approval workflow (Schedule/OT/Leave/Visit) • PG→Leader, Leader→BUH routing • BUH email-link approval (no login) — signed token, expire 7d • Hybrid: inline + detail view • Reject with mandatory reason • Admin override + audit • Notification on approval/reject | BE: Workflow Core integration or custom state machine, signed approval token, email link endpoint Mobile: approval list/detail (Leader) Web: approval list/detail (Admin override, BUH) DevOps: SendGrid setup QA: email link security testing | 26 | 26 | M9
S7 | 1A | Leave, OT & integration with Approval | • Create OT/Leave/Emergency leave requests • Emergency leave tied to check-out • Reason input • Status tracking • History view • Wire all into Approval Workflow | BE: Leave/OT entities, integration with Approval Mobile: request creation screens Web: Admin/BUH view QA: end-to-end approval flows | 16 | 16 | M8, M9
S8 | 1A | Team Monitoring & Audit Log | • PG/Leader Online list (Mobile + Web) • Status today (working/not-checked-in/checked-out/leave/no-schedule/review) • Manual refresh + last-update • Audit Log infrastructure (interceptors) • Audit views (Admin) | BE: real-time status query, SignalR optional, EF Core interceptor for audit Mobile: PG Online screen (Leader) Web: Team Monitoring + Audit Log UI QA: status accuracy | 16 | 18 | M12, M16
S9 | 1A | Admin Review & Notification (basic) | • Admin Review queue (face fail, GPS>300m, device change) • Review actions: approve/reject/note/request more • Effect on attendance status post-review • In-app notification (basic) • Push notification (FCM) • Email notification (basic templates VI+EN) | BE: Notification service, FCM integration, SendGrid templates, review action endpoints Mobile: notification handling, badge Web: review screens QA: notification delivery testing | 22 | 22 | M16, M14
S10 | 1A | Phase 1A polish + UAT prep | • Bug fixes from internal testing • Dashboard basic (PG/Leader Online + check-in today) • Attendance report basic • i18n review pass (VI+EN strings) • Performance baseline • Internal release build | BE: bug fixes, basic report queries Mobile: bug fixes, i18n polish Web: basic dashboard, i18n polish QA: regression test cycle 1 DevOps: production deployment, monitoring | 16 | 18 | M14, M15, all
S11 | 1B | Phase 1A feedback + Product Master + Form Builder skeleton | • 50% capacity: Phase 1A bug fixes from internal use • Product Master CRUD (Admin) • Form Engine: Form entity design • Form Builder UI skeleton (drag-drop or config) • Input type registry | BE: Product entity, Form schema design (JSONB), 12 input types Web: Form Builder UI (drag-drop with @dnd-kit) Mobile: bug fixes from 1A QA: 1A regression | 21 | 22 | M4, M10
S12 | 1B | Form Engine — Builder + Rules + Assignment | • Full 12+ input types: text/number/single/multi/dropdown/datetime/image-upload/camera/file/product/store/brand-SKU • Form rules config (all per PRD 6.10) • Assignment to role/user/store/area/category/product • Versioning on edit-after-publish | BE: Form rules engine, assignment logic, version logic Web: rules config UI, assignment UI Mobile: form rendering engine QA: rules combinations | 26 | 28 | M10
S13 | 1B | Form Engine — Rendering, Submit & Offline draft | • Mobile form rendering (all input types) • Offline draft storage (Hive) • Submit + retry on reconnect • Form templates: stock report, market report, product photo, PC checklist, free report • Scoring & test logic • Random questions/answers • Edit-after-submit per config | BE: form submission endpoint, scoring, idempotency keys Mobile: form renderer, offline draft (Hive), sync logic Web: form result viewer QA: offline scenarios, slow network | 26 | 28 | M10
S14 | 1B | Form templates remaining + Visit Plan | • Form: Survey, Training, Knowledge Test • Visit Plan list/create/detail (Mobile Leader) • BUH approval (web + email link) • Post-visit report via Form Engine • Visit Plan states | BE: visit plan entity, integration with Form Engine Mobile: visit plan screens (Leader) Web: BUH approval screens QA: end-to-end visit flow | 20 | 22 | M10, M11
S15 | 1B | Document Center + Notification full | • Public/Private folders • Admin upload + assignment • PDF/image/text support • Search by name • Payslip as private file per user • Notification: all event types per PRD 6.14 • Read confirmation for important news • Badge logic | BE: Document entity, S3/MinIO integration, signed URL, all notification events Mobile: document viewer, news with read confirm Web: document upload + news management QA: file security, signed URL expiry | 20 | 22 | M13, M14
S16 | 1B | Dashboard & Reports full + Export | • All Phase 1 reports per PRD 6.15: - Attendance, anomalies, face fail, GPS violation, fake GPS, schedule, leave/OT, pending approval, form submission, form pending, visit plan, test/survey results • Export per report (CSV/Excel) • Dashboard widgets | BE: report queries (optimized), export service (ClosedXML) Web: report screens, charts (Recharts), filters, export buttons QA: export accuracy, large dataset performance | 22 | 24 | M15
S17 | 1B | Hardening + Performance + Security audit | • Performance pass (BE: queries, indexes; Mobile: scroll perf; Web: bundle size) • Security review (OWASP top 10) • Penetration test self-check • Load testing baseline • i18n full review • Documentation update • Production runbook | BE: query optimization, indexes, rate limiting, CSP Mobile: profile mode test Web: lighthouse pass DevOps: backup strategy, monitoring alerts QA: load test (k6/Locust) | 16 | 20 | all
S18 | 1B | UAT + acceptance gate + bug fix only | • Full 35 acceptance criteria walkthrough with stakeholders • Bug fix only (NO new features) • User acceptance signatures • Final production release • Handover documentation • Training materials for end users | All hands: bug triage and fix QA: full regression DevOps: production release PM dev: stakeholder coordination, acceptance docs | 14 | 18 | all
|  | Total Sprint 0 + 1A |  |  | 199 | 212
|  | Total Phase 1B |  |  | 165 | 184
|  | GRAND TOTAL |  |  | 364 | 396
NOTE on dev-days
• Dev-days là tổng man-day cho TẤT CẢ work (BE + FE + Mobile + DevOps + QA) trong sprint đó.
• Với 2 devs × 22 ngày × 80% (sau khi trừ PM 20% và overhead) ≈ 35 dev-days/sprint capacity.
• Numbers in BLUE are direct inputs - bạn có thể chỉnh để re-estimate.
• Số ngày đã include buffer 20% cho risk. Nếu mọi thứ smooth, có thể nhanh hơn.
• Story points dùng Fibonacci: 1,2,3,5,8,13 cho từng task. Tổng/sprint ≈ 16-26.

## 04_Timeline
TIMELINE — Gantt view (each column = 1 week)
Sprint | Focus | Start (wk) | End (wk) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22
S0 | Setup | 1 | 2
S1 | Identity & Device | 3 | 4
S2 | Org & Assignment | 5 | 6
S3 | Attendance core | 7 | 8
S4 | Face Verification | 9 | 10
S5 | Work Schedule | 11 | 12
S6 | Approval Workflow | 13 | 14
S7 | Leave & OT | 15 | 16
S8 | Team Monitor + Audit | 17 | 18
S9 | Admin Review + Notif | 19 | 20
S10 | 1A Polish + Internal | 21 | 22
| ★ MILESTONE: Phase 1A Internal Release | [23 empty] | ★
Sprint | Focus | Start (wk) | End (wk) | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38
S11 | Feedback + Product + Form skel | 23 | 24
S12 | Form Builder + Rules | 25 | 26
S13 | Form Render + Offline | 27 | 28
S14 | Form templates + Visit Plan | 29 | 30
S15 | Document + Notif full | 31 | 32
S16 | Dashboard + Reports + Export | 33 | 34
S17 | Hardening + Security | 35 | 36
S18 | UAT + Acceptance Gate | 37 | 38
| ★ MILESTONE: Phase 1 Acceptance Gate (full nghiệm thu) | [17 empty] | ★
LEGEND
Setup phase
Phase 1A
Phase 1B
Milestone

## 05_Resources
RESOURCE ALLOCATION
TEAM MEMBERS
Role | Person | Dedicated % | Sprint capacity (days) | Phase 1 capacity (days) | Responsibilities
Senior Dev #1 (Tech Lead + PM) | TBD | 80% | 17.6 | 334.4 | Architecture, BE-lead, code review, PM duties (planning, stakeholder), DevOps
Senior Dev #2 (Full-stack) | TBD | 100% | 22 | 418 | Full-stack across BE/Web/Mobile as needed, QA, documentation
TOTAL TEAM CAPACITY |  |  | 39.6 | 752.4
Capacity check
Required dev-days (from Sprints) |  |  |  | 0
Available capacity (above) |  |  |  | 752.4
Utilization % |  |  |  | 0%
EXTERNAL / FREELANCE NEEDS
Role | When | Effort (days) | Day rate (M VND) | Total cost (M VND) | Notes
UI/UX Designer (freelance, optional) | Sprint 0-1 | 10 | 1.5 | 15 | Nếu cần UI polish ban đầu — có thể skip vì dev tự design
Security audit (freelance) | Sprint 17 | 3 | 3 | 9 | Pen test self-check trước nghiệm thu
Load test consultant | Sprint 17 | 2 | 2.5 | 5 | Optional, có thể tự làm với k6/Locust
App Store submission help | Sprint 18 | 2 | 1.5 | 3 | Optional — nếu chưa từng submit app
TOTAL EXTERNAL (M VND) |  |  |  | 32

## 06_Cost
COST BREAKDOWN — Phase 1 Total
All amounts in Million VND (M VND) unless stated. Inputs in BLUE. Yellow = key assumption.
ASSUMPTIONS (edit blue cells)
Senior dev monthly salary (gross) | 45 |  |  | M VND/month, Vietnam market 2026
Cost-to-company multiplier | 1.25 |  |  | Multiplier for BHXH, BHYT, thuế TNCN coverage, benefits
Cost per dev / month (CTC) | 56.25 |  |  | Cost to company (M VND/month)
Number of devs | 2 |  |  | —
Project duration (months) | 10 |  |  | Including Sprint 0
Effective working months | 10 |  |  | Devs paid full time throughout
1. PERSONNEL COST
Item | Monthly (M VND) | Months | Total (M VND) | Notes
2 Senior devs (CTC) | 112.5 | 10 | 1125 | 2 devs × cost/month × 10 months
Subtotal Personnel |  |  | 1125
2. INFRASTRUCTURE & SERVICES
Item | Monthly (M VND) | Months | Total (M VND) | Notes
VPS — Production (Vultr SG 8vCPU/16GB) | 1 | 10 | 10 | Estimate ~$40/month
VPS — Staging (smaller) | 0.5 | 10 | 5 | ~$20/month
Domain + SSL (Caddy auto) | 0.05 | 10 | 0.5 | ~600k/year amortized
PostgreSQL backups (object storage) | 0.2 | 10 | 2 | S3 storage cho daily backups
AWS S3 / MinIO for files | 0.5 | 10 | 5 | Hoặc MinIO self-host miễn phí trên VPS
Firebase Cloud Messaging | 0 | 10 | 0 | FREE tier đủ dùng
SendGrid / AWS SES email | 0.3 | 10 | 3 | ~100k-500k emails/month free, sau đó trả phí
FPT.AI Face Recognition | 1.5 | 10 | 15 | Estimate 500đ/verify × 3000 verifies/day = ~45k/day
Sentry error monitoring | 0.5 | 10 | 5 | Hoặc tự host miễn phí
GitHub Team | 0.2 | 10 | 2 | $4/user × 2
Other tools (Notion, Figma, etc.) | 0.5 | 10 | 5 | Productivity tools
Subtotal Infrastructure |  |  | 52.5
3. ONE-TIME COSTS
Item | Amount (M VND) |  |  | Notes
Apple Developer Account (yearly) | 2.5 |  | 2.5 | $99/year
Google Play Developer (one-time) | 0.65 |  | 0.65 | $25 one-time
Mac mini (refurbished, for iOS builds) | 28 |  | 28 | Hoặc thuê MacInCloud ~1.5tr/tháng
Test devices (1 iPhone + 1 Android low-end) | 8 |  | 8 | Bắt buộc test face/GPS thật
Development laptops (if not owned) | 0 |  | 0 | Giả sử devs đã có laptop
Subtotal One-time |  |  | 39.15
4. EXTERNAL / FREELANCE
From 05_Resources |  |  | 32 | Sum of external/freelance from Resources sheet
GRAND TOTAL
Subtotal (1+2+3+4) |  |  | 1248.65
Contingency % | 15% |  | 187.2975 | Buffer cho risk (recommend 10-20%)
TOTAL PHASE 1 BUDGET (M VND) |  |  | 1435.9475
TOTAL in Billion VND |  |  | 1.4359
USD/VND exchange rate | 25500
TOTAL in USD |  |  | 56311.6667
SCENARIO ANALYSIS
Scenario | Duration (months) | Personnel adj factor | Total est (M VND) | Notes
Best case (smooth, no major issues) | 9 | 90% | 1029.65
Base case (current plan) | 10 | 100% | 1435.9475
Worst case (major risk materializes) | 13 | 100% | 1617.9

## 07_Risks
RISK REGISTER
# | Category | Risk description | Impact (1-5) | Probability (1-5) | Score | Mitigation | Owner
1 | Tech | Face Recognition vendor accuracy không đủ tốt cho ánh sáng VN (cửa hàng tối, ngoài trời) | 4 | 3 | 12 | Test 2-3 vendors (FPT.AI, AWS Rekognition, VNG) trong Sprint 0; có fallback selfie + Admin review | Tech Lead
2 | Tech | Fake GPS detection cuộc đua không có điểm dừng — luôn có app/root bypass mới | 3 | 5 | 15 | Accept giới hạn: dùng plugin trust_location + EXIF check + selfie cross-verify; clear policy với users | Tech Lead
3 | Tech | Form Engine versioning logic phức tạp — bug có thể làm mất data | 5 | 3 | 15 | Design carefully, write extensive tests Sprint 12; immutable form versions trong DB; idempotency keys | Dev #2
4 | Tech | Offline draft sync conflicts (user submit nhiều version từ nhiều devices) | 3 | 3 | 9 | Hive với timestamp-based conflict resolution; force single-device login đã giảm risk này nhiều | Dev #2
5 | Tech | BUH email-link approval bị forward → người khác duyệt nhầm | 4 | 3 | 12 | Token signed với SHORT expiry (24h); log IP/user-agent; 2FA optional sau Phase 1 | Tech Lead
6 | Tech | PostgreSQL performance khi scale (5000+ PG check-in cùng giờ sáng) | 4 | 2 | 8 | Index sớm; partitioning attendance table by month; Redis cache cho online status; load test Sprint 17 | Tech Lead
7 | Tech | Apple App Store reject vì face recognition / GPS tracking privacy concerns | 4 | 3 | 12 | Privacy policy chi tiết Sprint 0; clear consent UI; submit early test build qua TestFlight Sprint 4 | Dev #2
8 | Team | 1 dev nghỉ ốm/nghỉ việc giữa dự án | 5 | 3 | 15 | Documentation thorough mỗi sprint; pair programming periodic; code review mọi PR | Both
9 | Team | Dev kiêm PM bị quá tải, mất 30%+ capacity thực tế (không phải 20%) | 4 | 4 | 16 | Build buffer 20% vào estimate; weekly capacity review; có thể thuê PM part-time sau Sprint 6 nếu cần | Tech Lead
10 | Team | Skill gap với Flutter / SignalR / Workflow Core nếu không quen | 3 | 3 | 9 | Sprint 0 dành 3-5 ngày cho training/PoC; chọn libraries có docs/community lớn | Both
11 | Scope | Stakeholder yêu cầu thêm feature trong Phase 1 (scope creep) | 5 | 4 | 20 | Strong change control: change request → impact assessment → đưa vào Phase 2 nếu không critical | PM dev
12 | Scope | PRD ambiguity: Form Engine conditional logic, custom report builder không rõ scope | 4 | 4 | 16 | List ambiguities trong Sprint 0 và clarify với stakeholder; chốt scope trước khi build | PM dev
13 | Scope | Phase 1A feedback yêu cầu rework lớn vào 1B | 4 | 3 | 12 | Limit Phase 1A internal release to small group; collect feedback có cấu trúc; triage carefully | PM dev
14 | Infra | VPS bị tấn công DDoS / downtime gây ảnh hưởng chấm công | 4 | 2 | 8 | Cloudflare proxy (miễn phí); HA setup sau Phase 1; daily backups; runbook | Tech Lead
15 | Infra | Chi phí face recognition vượt budget nếu volume cao | 3 | 3 | 9 | Theo dõi monthly; có thể switch self-host (face_recognition Python lib) nếu cần | Tech Lead
16 | Business | Mức ROI không đạt expectation → cắt Phase 1B | 4 | 2 | 8 | Phase 1A đứng độc lập được; có giá trị ngay cả khi Phase 1B bị cắt | Stakeholder
17 | Compliance | Lưu trữ ảnh selfie/face data — GDPR/Vietnam data privacy law | 4 | 3 | 12 | Encryption at rest; retention policy (xóa sau 90 ngày); user consent rõ ràng | Tech Lead
18 | Acceptance | Stakeholder không sign-off 35 acceptance criteria vì interpretation khác | 5 | 3 | 15 | Detailed acceptance criteria doc với screenshots/videos sample Sprint 17; demo sớm | PM dev
Score = Impact × Probability
≥15 = Critical
10-14 = High
5-9 = Medium
<5 = Low

## 08_TechDecisions
TECH DECISIONS & RATIONALE
Area | Decision | Alternatives considered | Rationale
Backend framework | .NET 8 (LTS) + ASP.NET Core | Python (FastAPI/Django), Node.js (NestJS), Go | Devs đã biết C#. .NET 8 chạy native trên Linux performance tốt. Hangfire, SignalR, EF Core mature cho yêu cầu approval workflow + real-time + audit log.
Database | PostgreSQL 16 | MySQL, SQL Server, MongoDB | Open-source, JSONB cho Form Engine schema flexibility, mature ecosystem, free.
Cache & Queue | Redis 7 | Memcached, RabbitMQ | Cache cho online status + Hangfire job queue + session. 1 tool 3 use cases.
Background jobs | Hangfire | Quartz.NET, custom | Built-in dashboard UI, persisted jobs, retry logic, free. Critical cho notification + form deadline checks.
Real-time | SignalR | WebSocket native, Socket.io via Node sidecar | Built into .NET, simple. Cho PG Online status updates.
Web Admin framework | Next.js 14 (App Router) | Vite + React, Angular, Nuxt/Vue | Mature, large community, Ant Design Pro template tốt cho admin dashboard, TypeScript first.
UI library Web | Ant Design Pro v5 | Material UI, Chakra, custom Tailwind | Built specifically cho admin dashboards. ProTable, ProForm, ProDescriptions tiết kiệm hàng tháng dev.
State management Web | TanStack Query + Zustand | Redux Toolkit, Recoil | TanStack cho server state, Zustand cho client state. Simple, no boilerplate.
Mobile framework | Flutter 3.x | React Native, native iOS+Android | Đã chốt. 1 codebase, performance tốt, camera/GPS plugins mature.
Mobile state | Riverpod 2.x | Bloc, Provider, GetX | Type-safe, testable, không cần BuildContext, ít boilerplate hơn Bloc.
Mobile networking | Dio + Retrofit (Flutter) | http package | Interceptors cho auth/logging, request cancellation, file upload progress.
Mobile local storage | Hive + Hive Generator | SQLite (sqflite), shared_preferences | Fast key-value, type-safe với code gen, đủ cho offline draft.
Authentication | Custom JWT + Refresh tokens | Auth0, Keycloak, IdentityServer | Internal product 1 customer, custom đơn giản hơn. Considerable: Keycloak nếu cần SSO sau.
Face Recognition | FPT.AI Face (primary), tested in S0 | AWS Rekognition, Azure Face, self-host (DeepFace, face_recognition) | FPT.AI: VN-tuned, rẻ hơn (~500đ/verify), low latency cho VN. Backup: AWS Rekognition.
Fake GPS detection | Flutter plugin trust_location + custom checks | MDM solution, native code | Plugin check mock_location flag (Android) + JailMonkey (iOS jailbreak). Accept limitations.
Push notification | Firebase Cloud Messaging (FCM) | OneSignal, AWS SNS | Free, universal iOS+Android, mature SDK Flutter.
Email | SendGrid (start), AWS SES (scale) | Mailgun, self-host Postfix | SendGrid: 100 emails/day free, easy templates. Switch SES khi volume tăng.
File storage | MinIO self-host on VPS | AWS S3, Cloudflare R2 | Self-host miễn phí cho phase 1 (1 customer scale). S3-compatible API, switch S3 sau dễ.
Reverse proxy | Caddy | Nginx, Traefik | Auto SSL renewal, config đơn giản, đủ tính năng cho team nhỏ.
Containerization | Docker + Docker Compose | Kubernetes, Podman, bare metal | Đủ cho 1-3 VPS. K8s overkill cho team 2 devs.
CI/CD | GitHub Actions | GitLab CI, Jenkins, CircleCI | Repo trên GitHub, free tier đủ, marketplace lớn.
Monitoring | Sentry (errors) + Uptime Kuma (uptime) | Datadog, New Relic, Grafana Cloud | Sentry free tier OK; Uptime Kuma self-host miễn phí.
Logging | Serilog → file + Sentry | ELK stack, Loki | Serilog standard cho .NET; ELK overkill cho 1 server.
API documentation | Swagger/OpenAPI auto-generated | Postman collection, manual | .NET built-in Swashbuckle, miễn phí.
Testing BE | xUnit + Moq + Testcontainers | NUnit, MSTest | Industry standard. Testcontainers cho integration test với real PostgreSQL.
Testing Mobile | flutter_test + integration_test | — | Built-in.
Testing Web | Vitest + Playwright (E2E) | Jest + Cypress | Vitest nhanh hơn Jest; Playwright multi-browser, mạnh hơn Cypress.
i18n strategy | Resource files (.resx) BE, react-i18next Web, ARB Flutter | Single i18n service | Native solutions per platform, integrate dễ hơn.
Multi-tenancy | NOT IMPLEMENTED (single tenant) | Schema-per-tenant, row-level | Internal product 1 customer. Có thể add sau nếu cần SaaS.